## Planilha1
BURNDOWN
Datas | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | Total: | Tempo estimado | Legenda:
Sprint 1 | DAY 0 | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14 | DAY 15 | DAY 16 | DAY 17 | DAY 18 | DAY 19 | DAY 20 | DAY 21 | DAY 22 | DAY 23 | DAY 24 | DAY 25 | DAY 26 | DAY 27 | DAY 28 | DAY 29 |  |  | Data de conclusão de tarefa
Kick off | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Pendente
Brainstorm | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | Data de aula
Filtragem de ideias | 0 | 3 | 1 | 0 | 0 | 1 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | 9 | 5
Visita | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | 0 | 0
Validação das ideias | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | 7 | 5
Refinamento das ideias | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | 6 | 3
Montagem da apresentação | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | 0 | 0
Propor as ideias | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | 0 | 0
Feedback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | 0 | 0
Relátorio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | Pen | 0 | 0